## Dades
Alumnes	Nom	Alias
Alumne 1	Irene Blanco Fabregat	Irene
Alumne 2	Juan Antonio Muñoz Fernandez	Juan

Horari	Hora entrada	Hora sortida	Hores totals
Dilluns	8:30	14:00	5
Dimarts	8:30	15:00	6
Dimecres	8:30	14:00	5
Dijous	8:30	15:00	6
Divendres	8:30	15:00	6

BD creation and insertions (5h)
JS and PHP objects creation (5h)
CU_01 Profile Administration (6h)
CU_02 User items administration (10h)
CU_03 Search items (6h)
CU_04 Exchange administration (10h)
CU_05 Bids Administration (10h)
CU_06 Evaluations (5h)
CU_07 Friends list administration (3h)
CU_08 Events assistance administration (3h)
CU_09 Logout (1h)
CU_10 Users administration (2h + 6h)
CU_11 Events administration(2h + 5h)
CU_12 Items administration (2h + 6h)
CU_13 Warnings administration (5h)
CU_14 Delete user account (2h)
CU_15 Register as a new user (2,5h)
CU_16 Login (2,5h)
CU_17 Start trade administration (6h)
CU_18 Search users (3h)
CU_19 Search items (3h)
CU_20 Bids administration (3h+6h)
CU_21 Search bids (3h)

## Setmana 1
Planning diari seguiment del mòdul de síntesi
Setmana 1	Dilluns 05/05/14			Dimarts 04/05/14			Dimecres 05/05/14			Dijous 08/05/14			Divendres 09/05/14
	8:30-14:00 (5h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan	8:30-14:00 (5h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan
Feina planificada	JS objects creation	1,5		DB check	4		CU_15	2,5		CU_09	1		CU_10	6
Feina planificada	PHP objects creation	3,5		CU_09	1		CU_16	2,5		CU_18	3		CU_01		6
Feina planificada	DB creation		2	CU_02		5	CU_02		5	CU_10	2
Feina planificada	DB insertion		1					CU_03		6
Feina planificada	Planning and real work		1
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Hores pendents		0	1		0	0		0	0		0	0		0	0
Feina real	JS objects creation	1,5		JS objects creation	1,5		CU_15	3,5		CU_10	6		CU_10	-
Feina real	PHP objects creation	1,5		PHP objects creation	1,5		CU_10	1,5		CU_12		6	CU_01		-
Feina real	DB creation		2	DB changes		1,5	CU_12		5
Feina real	DB insertion		1	Git preparation		1,5
Feina real	Planning and real work		1	CU_16		1,75
Feina real	Error corrections		1	CU_09		0,25
Feina real				CU_02		1
Feina real				CU_15	1
Feina real
Feina real
Feina real
Feina real
Hores pendents	Entrevista prácticas	2	0	Examen JSP	2	0		0	0		0	0		6	6
Observacions	We had problems to put the double / Primary keys but we was resolved in 10 minutes.					Problems in db with some special characters and accents

## Setmana 2
Planning diari seguiment del mòdul de síntesi
Setmana 2	Dilluns 4/05/14			Dimarts 13/05/14			Dimecres 14/05/14			Dijous 15/05/14			Divendres 16/05/14
	8:30-14:00 (5h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan	8:30-14:00 (5h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan
Feina planificada	CU_05	5		CU_05	6		CU_19	3		CU_12	6		CU_17	6
Feina planificada	CU_04		5	CU_04		6	CU_12	2		CU_21		3	CU_20		6
Feina planificada					CU_14		2	CU_20		3
Feina planificada					CU_07		3
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Hores pendents		0	0		0	0		0	0		0	0		0	0
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Hores pendents		5	5		6	6		5	5		6	6		6	6
Observacions

## Setmana 3
Planning diari seguiment del mòdul de síntesi
Setmana 3	Dilluns 19/05/14			Dimarts 20/05/14			Dimecres 21/05/14			Dijous 22/05/14			Divendres 23/05/14
	8:30-14:00 (5h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan	8:30-14:00 (5h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan
Feina planificada	CU_06	5		CU_11	5		Check all the functions	5		Style the app	6	6	Style the app	6	6
Feina planificada	CU_08		3	CU_13		5			5
Feina planificada	CU_11		2
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Hores pendents		0	0		1	1		0	0		0	0		0	0
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Hores pendents		5	5		6	6		5	5		6	6		6	6
Observacions

## Setmana 4
Planning diari seguiment del mòdul de síntesi
Setmana 4	Dilluns 26/05/14			Dimarts 27/05/14			Dimecres 28/05/14			Dijous 29/05/14			Divendres 30/05/14
	8:30-14:00 (5h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan	8:30-14:00 (5h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan	8:30-15:00 (6h)	Irene	Juan
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Feina planificada
Hores pendents		5	5		6	6		5	5		6	6		6	6
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Feina real
Hores pendents		5	5		6	6		5	5		6	6		6	6
Observacions